## Master Dashboard
DOPAMINE PATCHES — 90-DAY BUSINESS PLAN
March 23 – June 20, 2026 ¦ Owner: Alexander + Team
KEY PERFORMANCE INDICATORS
| Native Ads | Email | Instagram | Creators | Comment Rate | AOV / Upsell
Target | 5-10/day | 2-3/day | 2/day | 20+ | >90% | >15%
Metric | Ads Created & Tested | Emails Sent | Posts Published | Active Creators | Auto-Responses | Upsell Acceptance
PHASE TIMELINE
Phase | Dates | Focus
Foundation | Mar 23 – Apr 19 | Set up all systems, begin testing native ads, launch email flows, start IG content, build comment bot, install upsell apps
Growth | Apr 20 – May 17 | Scale ad testing, iterate on winners, optimize email flows, grow IG consistently, expand creator roster, A/B test upsells
Scale & Optimize | May 18 – Jun 20 | Double down on winning ads, full email segmentation, IG engagement loops, creator retainers, optimize AOV
OWNERSHIP SUMMARY
Workstream | Owner | Notes
Native Ads | Team | Daily ad creation + testing, Alexander provides AI prompt guide
Email Marketing | Team | Flows + campaigns in Klaviyo, Alexander provides swipe file examples
Instagram Organic | Team | Batch content creation + scheduling
Creator Management | Alexander | Insense inbound, weekly check-ins, sample shipping
Comment Responses | Team | Build AI agent, Alexander approves tone/responses
Upsell Testing | Team | Shopify app setup + A/B testing bundles

## Native Ads
NATIVE ADS — WORKSTREAM DETAIL
Static native ads on Meta ¦ 5-10 new ads/day ¦ Long-form copy + congruent AI images ¦ Owner: Team
OVERVIEW
Run static native ads from fake Facebook pages (e.g. 'Sarah Collins', 'Better Brain Tips') with AI-generated long-form copy (1200+ words) using the format: strong hook > hero placement > USP > objection handle > soft CTA. Each ad includes a congruent AI-generated image that looks organic ('shot on iPhone'). All ads go into a CBO for Meta to allocate spend. The text hook and image congruence are the two most critical elements. Alexander has a YouTube video guide with AI prompts for creating the copy effectively.
KEY PERFORMANCE INDICATORS
KPI | Description | Target | Notes
Ads Created/Day | New static native ads created and launched | 5-10/day | Each ad = copy + congruent AI image
Hook CTR | Click-through rate on ad hooks | >1.5% | Text hook is the #1 lever
CPA | Cost per acquisition from native ads | Track weekly | Measured at ad set level in CBO
Winners Found | Ads showing potential (low CPA, good CTR) | Track weekly | After testing phase, 50% of new ads iterate on these
Ad Spend | Daily budget allocated to native ad CBO | Track weekly | Meta allocates spend within CBO automatically
PHASE BREAKDOWN
Phase | Dates | Goals | Deliverables | Owner
Foundation | Mar 23 – Apr 19 | Set up ad creation workflow using AI prompt guide. Create fake pages (e.g. 'Sarah Collins', 'Better Brain Tips'). Begin producing 5-10 ads/day with long-form copy (1200+ words) and congruent AI images. Test a wide variety of hooks. | Ad creation SOP documented, 2+ fake pages live, 140-280 ads tested, hook performance data collected | Team
Growth | Apr 20 – May 17 | Analyze first 4 weeks of data. Identify any ads with potential (good CTR, lower CPA). Split new ad creation: 50% new hook/angle tests, 50% iterations on promising ads. Refine AI image style to match best-performing copy. | Performance report, top hooks identified, iteration templates created, 140-280 more ads tested | Team
Scale & Optimize | May 18 – Jun 20 | Heavy iteration on proven winners. Build out variations of best hooks with different images, copy angles, and page personas. Continue testing new concepts at 50% of volume. Document winning formulas for ongoing use. | Winning ad playbook, scaled winners in CBO, 90-day performance report | Team
WEEKLY TASK BREAKDOWN
Week | Dates | Task Description | Deliverable | Owner | Status
Week 1 | Mar 23-29 | Set up ad creation workflow from AI prompt YouTube guide. Create 2+ fake Facebook pages. Produce first batch of 5-10 ads/day: long-form copy (hook > hero > USP > objection handle > soft CTA) + congruent 'shot on iPhone' AI images. | SOP doc, fake pages live, 35-70 ads created | Team | Not Started
Week 2 | Mar 30-Apr 5 | Continue 5-10 ads/day. Focus on testing a wide variety of text hooks. Review initial CTR data to see which hooks get attention. | 70+ more ads live, early hook CTR data | Team | Not Started
Week 3 | Apr 6-12 | Continue volume. Begin cataloging which hook styles perform (curiosity, fear, story, claim). Ensure AI images are congruent with each ad's copy angle. | Hook style tracker started, 70+ more ads | Team | Not Started
Week 4 | Apr 13-19 | End of Foundation. Pull first full performance report. Identify any ads showing potential. Create a 'promising ads' shortlist to iterate on. | Month 1 report, promising ads shortlist | Team | Not Started
Week 5 | Apr 20-26 | Shift to 50/50 split: half new concepts, half iterations on promising ads. Iterate by changing hooks, images, or copy angles on winners. | Iteration batch 1 live, new concepts continue | Team | Not Started
Week 6 | Apr 27-May 3 | Continue 50/50 split. Test new image styles paired with proven hooks. Experiment with different fake page personas. | Image style tests, persona variations | Team | Not Started
Week 7 | May 4-10 | Refine iteration process. Double down on the specific hook formats and image styles showing best CPA. | Refined iteration templates | Team | Not Started
Week 8 | May 11-17 | End of Growth. Pull month 2 report. Identify confirmed winners and document what makes them work (hook type, image style, copy angle). | Month 2 report, winning formulas documented | Team | Not Started
Week 9 | May 18-24 | Scale phase begins. Heavy iteration on confirmed winners. Create 5+ variations of each winner with different hooks/images. | Winner variation batch 1 | Team | Not Started
Week 10 | May 25-31 | Continue scaling winners. Test new concepts at reduced volume (25-30% of daily output). Monitor CPA trends. | Scaled variations, CPA trend report | Team | Not Started
Week 11 | Jun 1-7 | Focus on building out the strongest ad 'families' (groups of variations around a winning formula). Keep fresh concepts flowing. | Ad family sets documented | Team | Not Started
Week 12 | Jun 8-14 | Final push on scaling. Lock in the best-performing ad families. Prepare 90-day report. | Final scaling batch | Team | Not Started
Week 13 | Jun 15-20 | Compile 90-day performance report. Document winning playbook: best hooks, image styles, copy angles, page personas for ongoing use. | 90-day report, Native Ads Playbook | Team | Not Started

## Creator Management
CREATOR MANAGEMENT — WORKSTREAM DETAIL
Insense inbound + creator relationships ¦ Owner: Alexander
OVERVIEW
Manage inbound creator applications through Insense, send samples to qualified creators, and run their UGC videos as ads. Creators whose videos generate sales get offered monthly retainers for a set number of videos. Alexander handles this directly — the main work is checking inbound applications a few times per week, copy-pasting onboarding messages, shipping samples, and doing weekly check-ins in a group chat. A creator brief with top-performing video examples is already created.
KEY PERFORMANCE INDICATORS
KPI | Description | Target | Notes
Active Creators | Creators who have received samples and are producing content | 20+ | Ramp up from current ~20 samples sent
Videos Received | UGC videos delivered by creators | Track weekly | Most will be low quality — volume matters
Conversion Rate | Creators whose videos generate a sale when run as ads | Track | Creators who convert get offered retainers
Retainer Creators | Creators on monthly retainer for set # of videos | Build over time | Only after proven sales from their content
Response Time | Time to respond to inbound Insense applications | < 48 hours | Check inbound a few times per week
PHASE BREAKDOWN
Phase | Dates | Goals | Deliverables | Owner
Foundation | Mar 23 – Apr 19 | Continue processing Insense inbound. Send samples to qualified creators. Follow up on 20 samples already sent. Collect first batch of videos. Run videos as ads to test conversions. | 40+ total samples sent, first videos received and tested as ads | Alexander
Growth | Apr 20 – May 17 | Ramp up sample volume. Identify creators whose videos drive sales. Begin retainer conversations with top performers. Maintain weekly check-ins in group chat. | 60+ samples sent, retainer offers to top creators, weekly check-in cadence | Alexander
Scale & Optimize | May 18 – Jun 20 | Lock in retainer deals with proven creators. Maintain inbound pipeline. Optimize brief based on what video styles convert best. | Retainer creators producing monthly content, optimized brief, 90-day report | Alexander
WEEKLY TASK BREAKDOWN
Week | Dates | Task Description | Deliverable | Owner | Status
Week 1 | Mar 23-29 | Review inbound Insense applications (a few times this week). Send onboarding messages + samples to qualified creators. Follow up with the ~20 creators who already received samples. | New samples shipped, follow-ups sent | Alexander | Not Started
Week 2 | Mar 30-Apr 5 | Continue processing inbound. Collect any delivered videos. Upload videos to ad account for testing. | Videos received and uploaded as ads | Alexander | Not Started
Week 3 | Apr 6-12 | Check inbound, ship samples. Review ad performance of creator videos. Note which creators' content is getting traction. | Updated creator tracker with ad performance | Alexander | Not Started
Week 4 | Apr 13-19 | Continue pipeline. 40+ samples should be out by now. Start identifying which video styles/creators drive lowest CPA. | Month 1 pipeline summary | Alexander | Not Started
Week 5-8 | Apr 20-May 17 | Maintain inbound processing a few times/week. Weekly group chat check-ins with active creators. Reach out to top performers about monthly retainer deals (set # of videos for fixed fee). Keep shipping samples. | Retainer offers sent, weekly check-ins happening, 60+ samples out | Alexander | Not Started
Week 9-13 | May 18-Jun 20 | Lock in retainer agreements. Continue inbound pipeline. Refine creator brief based on what converts. Compile 90-day creator performance report. | Active retainers, optimized brief, 90-day report | Alexander | Not Started

## Email Marketing
EMAIL MARKETING — WORKSTREAM DETAIL
Klaviyo ¦ 2-3 campaigns/day (segmented) ¦ 10 new templates/week ¦ Owner: Team
OVERVIEW
Send 2-3 segmented broadcast campaigns per day and create 10 new email templates per week based on existing supplement brand email examples from Alexander's inbox. Flows are automated and more important to get right first — the 5 priority flows are: Welcome Series, Abandoned Cart, Abandoned Browse, Abandoned Checkout, and Post-Purchase. Campaigns are segmented by audience so not every subscriber receives every email. Alexander has a large collection of example emails from a successful supplement brand to use as a swipe file.
KEY PERFORMANCE INDICATORS
KPI | Description | Target | Notes
Emails/Day | Broadcast campaigns sent per day | 2-3 campaigns | Segmented — not every subscriber gets every email
Templates/Week | New email templates created from swipe file | 10 new templates | Based on existing supplement brand email examples
Open Rate | Average email open rate across campaigns | >35% | Track by segment
Click Rate | Average click-through rate | >2.5% | Track by segment
Revenue/Email | Revenue attributed per email sent | >$0.10/recipient | Klaviyo attribution
List Growth | Net new subscribers per week | Tracked weekly | From ads, site traffic, popups
PHASE BREAKDOWN
Phase | Dates | Goals | Deliverables | Owner
Foundation | Mar 23 – Apr 19 | Set up core Klaviyo flows: Welcome Series, Abandoned Cart, Abandoned Browse, Abandoned Checkout, Post-Purchase. Create first 30 email templates from swipe file. Begin sending 2-3 segmented campaigns/day. | 5 core flows live, 30 templates created, daily campaign cadence started | Team
Growth | Apr 20 – May 17 | Continue 10 templates/week. Build out list segments. A/B test subject lines and send times. Analyze flow performance and optimize. Improve deliverability. | Segments built, 40+ new templates, A/B test results, flow optimization report | Team
Scale & Optimize | May 18 – Jun 20 | Full segmentation live. Launch re-engagement flow for inactive subscribers. Win-back campaigns. Suppression list management. 90-day performance report. | All segments optimized, re-engagement flow, win-back campaign, final report | Team
WEEKLY TASK BREAKDOWN
Week | Dates | Task Description | Deliverable | Owner | Status
Week 1 | Mar 23-29 | Audit existing Klaviyo account (lists, segments, any existing flows). Set up Welcome Series flow (5 emails). Set up Abandoned Cart flow (3 emails). Create first 10 email templates from swipe file. | Audit complete, 2 flows live, 10 templates | Team | Not Started
Week 2 | Mar 30-Apr 5 | Set up Abandoned Browse flow (3 emails). Set up Abandoned Checkout flow (3 emails). Create 10 new templates. Begin daily campaign sends (start at 2/day). | 2 more flows live, 20 total templates, campaigns started | Team | Not Started
Week 3 | Apr 6-12 | Set up Post-Purchase flow (4 emails). Scale to 2-3 campaigns/day. Create 10 new templates. Analyze open/click rates from first 2 weeks. | All 5 core flows live, 30 templates, performance data | Team | Not Started
Week 4 | Apr 13-19 | Continue 2-3 campaigns/day. Create 10 new templates. Pull Month 1 report: flow performance, campaign performance, list growth. Identify best-performing templates. | Month 1 report, 40 templates, top performers identified | Team | Not Started
Week 5 | Apr 20-26 | Build audience segments (by purchase history, engagement, signup source). Begin A/B testing subject lines. Create 10 new templates. | Segments created, A/B tests launched, 50 templates | Team | Not Started
Week 6 | Apr 27-May 3 | A/B test send times. Optimize flows based on Month 1 data (update underperforming emails). Create 10 new templates. | Send time data, flow updates, 60 templates | Team | Not Started
Week 7 | May 4-10 | Continue segmented campaigns. Review A/B test results and implement winners. Create 10 new templates. Check deliverability (spam rates, bounce rates). | A/B winners implemented, deliverability report, 70 templates | Team | Not Started
Week 8 | May 11-17 | Month 2 report. Optimize segments based on engagement data. Create 10 new templates. Refine campaign calendar. | Month 2 report, optimized segments, 80 templates | Team | Not Started
Week 9 | May 18-24 | Build re-engagement flow for inactive subscribers. Set up suppression lists. Create 10 new templates. | Re-engagement flow live, suppression lists active, 90 templates | Team | Not Started
Week 10 | May 25-31 | Launch win-back campaign for lapsed customers. Continue daily campaigns. Create 10 new templates. | Win-back campaign live, 100 templates | Team | Not Started
Week 11 | Jun 1-7 | Full segmentation audit. Ensure all subscribers are in correct segments. Create 10 new templates. Optimize underperforming flows. | Segmentation audit complete, 110 templates | Team | Not Started
Week 12 | Jun 8-14 | Final flow optimizations. Create 10 new templates. Prepare 90-day report data. | Final optimizations, 120 templates | Team | Not Started
Week 13 | Jun 15-20 | Compile 90-day email performance report: revenue attribution, flow performance, top campaigns, segment analysis, deliverability. Document SOPs. | 90-day report, Email Marketing SOP | Team | Not Started

## Instagram Organic
INSTAGRAM ORGANIC — WORKSTREAM DETAIL
Educational static content ¦ 2 posts/day ¦ AI-generated ¦ Owner: Team
OVERVIEW
Build out the Instagram page (currently 700 followers, zero posts) with easy-to-create educational content about the product — transdermal delivery, ingredients, how patches work, etc. Focus on static posts that can be batch created and scheduled. No reels for now (video bandwidth goes to ads). Priority is shareable content: educational slides, discussion posts, customer comment screenshots. Set up profile highlights (How to Use, The Science, FAQs). Content should be AI-generated and template-based for efficient batch creation.
KEY PERFORMANCE INDICATORS
KPI | Description | Target | Notes
Posts/Day | Static posts published per day | 2/day | Batch created and scheduled in advance
Shares/Post | Average shares per post | Track weekly | Shareability is the key engagement metric
Follower Growth | Net new followers per week | Track weekly | Starting from 700 followers, no prior posts
Content Templates | Number of reusable content formats | 5+ | Discussion, educational slides, customer comments, etc.
Highlights | Profile highlights set up | 3+ | How to Use, The Science, FAQs at minimum
PHASE BREAKDOWN
Phase | Dates | Goals | Deliverables | Owner
Foundation | Mar 23 – Apr 19 | Create 5+ content templates (educational slides, discussion posts, customer comment screenshots, etc.). Batch create first 2 weeks of content. Set up profile highlights (How to Use, The Science, FAQs). Begin posting 2/day. | Content templates created, highlights live, 2/day posting started, 60+ posts published | Team
Growth | Apr 20 – May 17 | Continue 2/day. Analyze which content formats get the most shares. Double down on shareable formats. Build 2-week content buffer. Refine AI-generated educational content around transdermal delivery, ingredients, etc. | Share data analysis, refined templates, consistent 2/day with buffer | Team
Scale & Optimize | May 18 – Jun 20 | Optimize content mix based on share/engagement data. Maintain 2/day cadence. Experiment with carousel posts. Build evergreen content library for ongoing use. 90-day report. | Optimized content mix, evergreen library, 90-day report | Team
WEEKLY TASK BREAKDOWN
Week | Dates | Task Description | Deliverable | Owner | Status
Week 1 | Mar 23-29 | Design 5+ content templates: educational slides (transdermal delivery, ingredients, how patches work), discussion/question posts, positive customer comment screenshots, product benefit infographics. Set up scheduling tool. | 5+ templates designed, scheduling tool set up | Team | Not Started
Week 2 | Mar 30-Apr 5 | Batch create first 2 weeks of content using templates. Set up profile highlights: How to Use, The Science, FAQs. Begin posting 2/day. | Highlights live, 14+ posts scheduled, posting started | Team | Not Started
Week 3 | Apr 6-12 | Continue 2/day posting. Batch create next week's content. Track which posts get shares vs. just likes. Note what formats perform. | Consistent posting, early engagement data | Team | Not Started
Week 4 | Apr 13-19 | Continue posting. Pull Month 1 report: follower growth, shares, top-performing post formats. Batch create next 2 weeks. | Month 1 report, content buffer built | Team | Not Started
Week 5-6 | Apr 20-May 3 | Double down on most-shared content formats. Create more educational content around the science (transdermal delivery, bioavailability, ingredient breakdowns). Maintain 2/day. | Refined content mix, educational series started | Team | Not Started
Week 7-8 | May 4-17 | Continue refined posting. Experiment with carousel posts for educational content. Month 2 report. Maintain 2-week content buffer. | Carousel tests, Month 2 report | Team | Not Started
Week 9-10 | May 18-31 | Optimize content mix based on 2 months of data. Focus on evergreen educational content that can be reused. Maintain 2/day. | Optimized mix, evergreen content started | Team | Not Started
Week 11-12 | Jun 1-14 | Build evergreen content library (best-performing posts that can be recycled). Continue daily posting. Prepare 90-day data. | Evergreen library, consistent posting | Team | Not Started
Week 13 | Jun 15-20 | Compile 90-day IG report: follower growth, top formats, share rates, content library inventory. Document content creation SOP. | 90-day report, IG Content SOP | Team | Not Started

## Comment Responses
COMMENT RESPONSES — WORKSTREAM DETAIL
AI agent for ad comment replies ¦ Owner: Team
OVERVIEW
Build an AI agent that automatically responds to comments on all ad posts. The agent should answer questions and provide informative, realistic, and friendly responses that push inquisitive commenters toward a purchase. No need to like comments or audit response times — the focus is on helpful, conversion-oriented replies. The agent should be built and deployed within 2 weeks, then run autonomously with weekly spot-checks.
KEY PERFORMANCE INDICATORS
KPI | Description | Target | Notes
Response Rate | % of ad comments that receive a response | >90% | Agent should catch all inquisitive comments
Response Quality | Accuracy and helpfulness of AI responses | Spot-check weekly | Friendly, informative, realistic tone
Conversion Assist | Comments where response helps push toward purchase | Track | Measure click-throughs from comment replies
PHASE BREAKDOWN
Phase | Dates | Goals | Deliverables | Owner
Build | Mar 23 – Apr 5 | Research and select AI agent tool (Manus, Claude, or other). Build the comment response agent. Train it on product knowledge, FAQs, common objections. Define tone: friendly, informative, realistic. Test on sample comments. | Agent built, trained, and tested on sample comments | Team
Launch & Monitor | Apr 6 – Apr 19 | Deploy agent on all active ad posts. Monitor response quality for first 2 weeks. Adjust tone and knowledge base as needed. Alexander approves response style. | Agent live on all ads, quality verified, adjustments made | Team
Maintain | Apr 20 – Jun 20 | Agent runs autonomously. Spot-check response quality weekly. Update knowledge base if new products or FAQs emerge. Monthly performance check. | Ongoing autonomous operation, weekly spot-checks | Team
WEEKLY TASK BREAKDOWN
Week | Dates | Task Description | Deliverable | Owner | Status
Week 1 | Mar 23-29 | Research AI agent options (Manus, Claude, or other tools). Select tool. Begin building the comment response agent. Feed it product knowledge: ingredients, how patches work, pricing, shipping, FAQs. | Tool selected, agent build started, knowledge base created | Team | Not Started
Week 2 | Mar 30-Apr 5 | Finish building agent. Train on common comment types: questions about ingredients, 'does this actually work?', shipping questions, pricing objections. Define response tone: friendly, informative, realistic — gently push toward purchase. Test on sample comments. | Agent built and tested, response tone approved by Alexander | Team | Not Started
Week 3 | Apr 6-12 | Deploy agent on all active ad posts. Monitor responses closely — check every response for accuracy and tone. Fix any issues. | Agent live, all responses reviewed | Team | Not Started
Week 4 | Apr 13-19 | Continue monitoring. Reduce review to spot-checks (20-30% of responses). Update knowledge base for any gaps found. Pull first performance report. | Spot-check process established, performance report | Team | Not Started
Week 5+ | Apr 20-Jun 20 | Agent runs autonomously. Weekly spot-check of 10-15 responses. Update knowledge base monthly or when new products/info added. Monthly performance summary. | Ongoing autonomous operation, monthly reports | Team | Not Started

## Upsell Testing
UPSELL TESTING — WORKSTREAM DETAIL
Shopify upsells + bundles ¦ A/B testing ¦ Owner: Team
OVERVIEW
Test different upsell strategies on Shopify to increase average order value. We have multiple patch products that can be bundled with the Dopamine Patch. Use Shopify apps to A/B test popups, cart upsells, product page cross-sells, and post-purchase offers at different price points and bundle combinations.
KEY PERFORMANCE INDICATORS
KPI | Description | Target | Notes
AOV | Average order value | Track weekly | Baseline vs. with upsells
Upsell Acceptance | % of customers who accept an upsell offer | >15% | Across all upsell types (popup, cart, post-purchase)
Revenue per Session | Total revenue divided by total sessions | Track weekly | Measures overall monetization improvement
Bundle Attach Rate | % of orders that include a bundle | Track | Dopamine patch + other patch bundles
PHASE BREAKDOWN
Phase | Dates | Goals | Deliverables | Owner
Foundation | Mar 23 – Apr 19 | Research and install Shopify upsell apps. Create bundle product pages (dopamine patch + other patches). Set up first A/B tests: cart upsell popup vs. no popup. Create 2-3 bundle offers at different price points. | Upsell app installed, bundle pages live, first A/B test running | Team
Growth | Apr 20 – May 17 | Analyze A/B test results. Test different upsell placements: cart page popup, product page cross-sell, post-purchase upsell. Test different bundle combinations and price points. | A/B test results, multiple upsell placements tested, winning bundles identified | Team
Scale & Optimize | May 18 – Jun 20 | Implement winning upsell strategies across the site. Optimize bundle pricing and positioning. Test post-purchase upsell flows. 90-day AOV impact report. | Optimized upsell system, AOV lift documented, 90-day report | Team
WEEKLY TASK BREAKDOWN
Week | Dates | Task Description | Deliverable | Owner | Status
Week 1 | Mar 23-29 | Research Shopify upsell/A/B testing apps (e.g., ReConvert, CartHook, Zipify OCU, Bold Upsell). Install chosen app. Set up baseline AOV tracking. | App installed, baseline AOV recorded | Team | Not Started
Week 2 | Mar 30-Apr 5 | Create bundle product pages: Dopamine Patch + other patch products at 2-3 price tiers. Design cart upsell popup offer. Launch first A/B test (cart popup vs. control). | Bundle pages live, A/B test #1 launched | Team | Not Started
Week 3 | Apr 6-12 | Monitor A/B test. Set up product page cross-sell section ('Frequently bought together'). Create post-purchase upsell offer. | Cross-sell section live, post-purchase offer ready | Team | Not Started
Week 4 | Apr 13-19 | Pull A/B test #1 results. Launch test #2 based on learnings. Pull Month 1 AOV report. | Test #1 results, test #2 launched, Month 1 report | Team | Not Started
Week 5-6 | Apr 20-May 3 | Test different bundle combinations (which patches pair best). Test different upsell copy and discount levels. Analyze which upsell placement converts best. | Bundle performance data, placement comparison | Team | Not Started
Week 7-8 | May 4-17 | Implement winning upsell placements. Optimize bundle pricing based on data. Month 2 report with AOV trend. | Winners implemented, Month 2 report | Team | Not Started
Week 9-10 | May 18-31 | Test post-purchase upsell flow (offer after checkout). Refine cart upsell based on 2 months of data. | Post-purchase flow tested, cart upsell optimized | Team | Not Started
Week 11-12 | Jun 1-14 | Final optimizations. Ensure all winning strategies are fully implemented. Prepare 90-day data. | All upsells optimized and live | Team | Not Started
Week 13 | Jun 15-20 | Compile 90-day upsell report: AOV lift, upsell acceptance rates, best-performing bundles, revenue impact. Document upsell strategy playbook. | 90-day report, Upsell Playbook | Team | Not Started